## Project (Detailed Version)
Implementation Project Progress Tracking
I. Project Basic Information
Project Name |  |  | Implementation Technology |  | Client Representative (Party A) |  |  |  | Sales Assistant |  |  |  | Implementation Days | 5 |  | Project Start Date | 2026-10-24 | Reporting Date | 2026-10-23 | End Progress | Project Schedule Timeline
II. Project Breakdown & Schedule Plan | [15 empty] | Planned Implementation Time | 2026-10-24 | Planned End Time | 2026-10-28 |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
No. | Project Phase | Task Name | Subtask | Estimated Workload | Importance | Materials Required | Responsible (R) | Approver (A) | Collaborator (S) | Support (C) | Informed (I) | Key Milestone |  |  | Completion Progress | Risk Alert & Remarks |  | Planned Start Date | Planned End Date | Actual Completion Date | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04
1 | Initiation | Project Kickoff |  |  | Normal |  | 梁建宁 |  |  |  | Required | CRM basic info obtained; client contacted for general briefing |  |  | Completed |  |  | 2026-10-21 | 2026-10-21 | 2026-10-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 |  | Preliminary Preparation (Site Survey) | Requirements Research | 30 min | Important |  | Required | Required |  | 杨杰文 |  | Confirm client requirements and finalize implementation plan |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 |  |  | Site Entry Agreement Signing | 30 min | Important | Site Entry Agreement | Required | Required |  |  |  | Sign site entry agreement |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 |  |  | Goods Inventory Check | 30 min | Very Important | Goods Receipt Note | Required | Required |  | 王凌云 |  | Sign goods receipt note |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Planning | Implementation Plan Confirmation | Develop and confirm work plan | 30 min | Important |  | Required |  |  |  | Required |  |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Execution | Network Debugging / Network Delivery | LAN Debugging | 1 hour | Very Important |  | Required |  | Required | 梁建宁 |  | Network runs normally across the whole venue |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 |  | Software Deployment | Server Deployment | 2 hours | Very Important |  | Required |  |  | 梁建宁 |  | Youcaihua service starts normally |  |  | Not Started |  |  | 2026-10-24 | 2026-10-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2 |  |  | Cashier Counter Deployment / Office PC Deployment | 1 hour | Very Important |  | Required |  |  | 梁建宁 |  |  |  |  | Not Started |  |  | 2026-10-26 | 2026-10-26 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 |  | Hardware Installation | Card terminal configured and tested | 1-3 days | Very Important | Electric drill, power strip, wireless network | Required | Required | Required | 周相勇 |  | Card terminal works normally |  |  | Not Started |  |  | 2026-10-24 | 2026-10-26 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 |  |  | Self-service equipment configured and tested | 0.5 day | Very Important | Network (Ethernet cable) | Required | Required | Required | 黄泓元 |  | Self-service equipment works normally |  |  | Not Started |  |  | 2026-10-26 | 2026-10-26 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3 |  |  | Access control equipment configured and tested | 1-2 days | Very Important | Reserved cable ducts, Ethernet cable | Required | Required | Required | 吴小杰 |  | Access control equipment works normally |  |  | Not Started |  |  | 2026-10-25 | 2026-10-26 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 |  |  | POS machine configured and tested | 1 hour | Very Important | Wireless WiFi or 4G network | Required | Required | Required | 叶其盛 |  | POS machine functions normally |  |  | Not Started |  |  | 2026-10-26 | 2026-10-26 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 |  |  | Billiards terminal configured and tested | 1-2 days | Very Important | Electric drill, wireless network | Required | Required | Required | 吴小杰 |  | Billiards terminal works normally |  |  | Not Started |  |  | 2026-10-24 | 2026-10-25 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.6 |  |  | Interactive check-in configured and tested | 1-3 days | Very Important | Wireless network, electric drill | Required | Required | Required | 高晓钦 |  | Interactive check-in tasks set up and playable normally |  |  | Not Started |  |  | 2026-10-24 | 2026-10-26 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.7 |  |  | Ambience system installed and debugged | 1-2 days | Important | TV, speaker system, LED strip, power supply | Required | Required | Required | 高晓钦 |  | Ambience system works normally |  |  | Not Started |  |  | 2026-10-24 | 2026-10-25
7.1 |  | System Content Initialization | Payment Method Configuration | 30 min | Very Important | Payment configuration materials | Required |  | Required | Required | Required | Payment function tested normally |  |  | Not Started |  |  | 2026-10-27 | 2026-10-27 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 |  |  | Mini-APP feature enabled and authorized | 30 min | Very Important | Mini-program administrator | Required |  | Required | Required | Required | Mini-program functions normally |  |  | Not Started |  |  | 2026-10-27 | 2026-10-27 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 |  |  | Assist client in completing package setup | 0.5 day | Very Important |  | Required | Required |  | 梁建宁 | (Owner) | Package launch completed |  |  | Not Started |  |  | 2026-10-27 | 2026-10-27 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4 |  |  | Data Import (for Replacement System only) | 3 hours | Very Important |  | Required | Required | Required | 高晓钦/黄植丰 |  | Historical data import completed |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | System Training | Front-desk Training / Back-office Training | 1-2 days | Very Important | Training sign-in sheet "Product User Manual" | Required | Required | Required | 高晓钦 |  | Cashiers use the system normally on duty and sign the training attendance |  |  | Not Started |  |  | 2026-10-27 | 2026-10-27 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Operation Process Testing & Acceptance | Overall process testing & verification | 0.5 day | Very Important |  | Required | Required |  | 梁建宁 |  |  |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Opening Support | On-site opening support | 1 day | Normal |  | Required |  |  |  | Required |  |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Acceptance | Material Handover | Network status handover, material handover, document handover, service manual handover | 1 hour | Important | Project Handover Form | Required | Required |  |  | (Owner) | Sign project handover form and hand over Youcaihua service manual |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.2 |  | Acceptance Form Handover | Sign acceptance form | 1 hour | Important | Project Acceptance Form | Required | Required |  |  | 梁建宁 | Sign project acceptance form |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.3 |  | Sales Handover | Sales Follow-up Visit | 1 hour | Normal |  | Required |  | Required | Sales Assistant | Sales Assistant | Follow-up visit completed |  |  | Not Started |  |  | 2026-10-28 | 2026-10-28 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes: 1. Work hours are measured in hours. 2. Completion progress is marked as Not Started, In Progress, Completed, and Not Required; different statuses update the corresponding colors. 3. The project schedule chart clearly shows the timeline and allows you to review the progress.
Note on H3: Fat丶宁: 填写实施人员后，自动更下到干系人表中，如部分信息需要调整可直接修改干系人内容
Note on L3: Fat丶宁: 填写甲方负责人后，自动更下到干系人表中，如部分信息需要调整可直接修改干系人内容

## Project (Concise Version)
Implementation Project Plan
No. | Project Phase | Task Name | Subtask | Estimated Workload | Importance | Key Milestone | Completion Progress | Risk Alert & Remarks | Planned Start Date | Planned End Date | Actual Completion Date
1 | Initiation | Project Kickoff |  |  | Normal | CRM basic info obtained; client contacted for general briefing | Completed | None | 2026-10-21 | 2026-10-21 | 2026-10-21
2.1 |  | Preliminary Preparation (Site Survey) | Requirements Research | 30 min | Important | Confirm client requirements and finalize implementation plan | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
2.2 |  |  | Site Entry Agreement Signing | 30 min | Important | Sign site entry agreement | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
2.3 |  |  | Goods Inventory Check | 30 min | Very Important | Sign goods receipt note | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
3 | Planning | Implementation Plan Confirmation | Develop and confirm work plan | 30 min | Important |  | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
4 | Execution | Network Debugging / Network Delivery | LAN Debugging | 1 hour | Very Important | Network runs normally across the whole venue | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
5.1 |  | Software Deployment | Server Deployment | 2 hours | Very Important | Youcaihua service starts normally | Not Started | None | 2026-10-24 | 2026-10-24 | Not Ended
5.2 |  |  | Cashier Counter Deployment / Office PC Deployment | 1 hour | Very Important |  | Not Started | None | 2026-10-26 | 2026-10-26 | Not Ended
6.1 |  | Hardware Installation | Card terminal configured and tested | 1-3 days | Very Important | Card terminal works normally | Not Started | None | 2026-10-24 | 2026-10-26 | Not Ended
6.2 |  |  | Self-service equipment configured and tested | 0.5 day | Very Important | Self-service equipment works normally | Not Started | None | 2026-10-26 | 2026-10-26 | Not Ended
6.3 |  |  | Access control equipment configured and tested | 1-2 days | Very Important | Access control equipment works normally | Not Started | None | 2026-10-25 | 2026-10-26 | Not Ended
6.4 |  |  | POS machine configured and tested | 1 hour | Very Important | POS machine functions normally | Not Started | None | 2026-10-26 | 2026-10-26 | Not Ended
6.5 |  |  | Billiards terminal configured and tested | 1-2 days | Very Important | Billiards terminal works normally | Not Started | None | 2026-10-24 | 2026-10-25 | Not Ended
6.6 |  |  | Interactive check-in configured and tested | 1-3 days | Very Important | Interactive check-in tasks set up and playable normally | Not Started | None | 2026-10-24 | 2026-10-26 | Not Ended
6.7 |  |  | Ambience system installed and debugged | 1-2 days | Important | Ambience system works normally | Not Started | None | 2026-10-24 | 2026-10-25 | Not Ended
7.1 |  | System Content Initialization | Payment Method Configuration | 30 min | Very Important | Payment function tested normally | Not Started | None | 2026-10-27 | 2026-10-27 | Not Ended
7.2 |  |  | Mini-APP feature enabled and authorized | 30 min | Very Important | Mini-program functions normally | Not Started | None | 2026-10-27 | 2026-10-27 | Not Ended
7.3 |  |  | Assist client in completing package setup | 0.5 day | Very Important | Package launch completed | Not Started | None | 2026-10-27 | 2026-10-27 | Not Ended
7.4 |  |  | Data Import (for Replacement System only) | 3 hours | Very Important | Historical data import completed | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended
8 |  | System Training | Front-desk Training / Back-office Training | 1-2 days | Very Important | Cashiers use the system normally on duty and sign the training attendance | Not Started | None | 2026-10-27 | 2026-10-27 | Not Ended
9 |  | Operation Process Testing & Acceptance | Overall process testing & verification | 0.5 day | Very Important |  | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended
10 |  | Opening Support | On-site opening support | 1 day | Normal |  | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended
10.1 | Acceptance | Material Handover | Network status handover, material handover, document handover, service manual handover | 1 hour | Important | Sign project handover form and hand over service manual | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended
10.2 |  | Acceptance Form Handover | Sign acceptance form | 1 hour | Important | Sign project acceptance form | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended
10.3 |  | Sales Handover | Sales Follow-up Visit | 1 hour | Normal | Follow-up visit completed | Not Started | None | 2026-10-28 | 2026-10-28 | Not Ended